## IT Risk Assessment Matrix
IT RISK ASSESSMENT MATRIX TEMPLATE
REF/ID | RISK TYPE | ASSET | RISK DESCRIPTION | RISK SEVERITY | RISK LIKELIHOOD | INTERNAL IMPACT | USER IMPACT | TRIGGER | MITIGATIONS / REMEDIES | ASSET | RISK SEVERITY KEY | RISK LIKELIHOOD KEY | RISK LEVEL KEY
9 | Tools | EXTERNAL | No access to programming tools | UNDESIRABLE | IMPROBABLE | MEDIUM | LOW | Unprepared workforce | Help download the software | EXTERNAL | ACCEPTABLE | IMPROBABLE | LOW
8 | Technology | EXTERNAL | No access to programming language | UNDESIRABLE | IMPROBABLE | MEDIUM | LOW | Unprepared Workforce | Help download the programming language | INSIDER | TOLERABLE | POSSIBLE | MEDIUM
6 | People | INSIDER | Improperly divided types of task | UNDESIRABLE | POSSIBLE | LOW | MEDIUM | Unorganized Organizer | Reorganize the organization | TRUSTED INSIDER | UNDESIRABLE | PROBABLE | HIGH
7 | Requirements | INSIDER | No reaching the goal of the module | INTOLERABLE | POSSIBLE | EXTREME | EXTREME | Mismanaged workforce | Reevaluate the goal and redistribute tasks |  | INTOLERABLE |  | EXTREME
5 | People | TRUSTED INSIDER | Uncooperative work force | UNDESIRABLE | POSSIBLE | EXTREME | HIGH | Unwilling Workforce | Redistribute tasks
1 | Estimation | INSIDER | No time to complete task | INTOLERABLE | PROBABLE | EXTREME | EXTREME | Mismanaged Workforce | add help to the task
2 | Estimation | TRUSTED INSIDER | Improper estimation of work | TOLERABLE | PROBABLE | LOW | LOW | Unorganized Organizer | Reevaluate goals
4 | Organizational | INSIDER | Poorly divided work on work force | TOLERABLE | PROBABLE | LOW | LOW | Unorganized Organizer | Redistribute tasks
3 | Organizational | INSIDER | Hard to understand documentation | TOLERABLE | PROBABLE | LOW | MEDIUM | Rushed Documentation | Spend more time on the documentaiton
CLICK HERE TO CREATE IN SMARTSHEET

## -Disclaimer-
Any articles, templates, or information provided by Smartsheet on the website are for reference only. While we strive to keep the information up to date and correct, we make no representations or warranties of any kind, express or implied, about the completeness, accuracy, reliability, suitability, or availability with respect to the website or the information, articles, templates, or related graphics contained on the website. Any reliance you place on such information is therefore strictly at your own risk.